## Sheet1
Tasks |  | Preformed by | Actual Time (hours) |  | Next Weeks Plans Under This Table
ID | Description |  | Task | Total
| Class Meeting | All | 2.5 | 2.5
| Sick time | Corey | 2 | 2
| Team Meeting | All | 1.5 | 1.5
| Reseach Electronic BoL Solutions | Corey | 1 | 1
Totals |  |  | 7 | 7
Plans for next week
Tasks |  | Preformed by | Actual Time (hours)
ID | Description |  | Task | Total
| Interview with Mr.Concepion | Corey | 0.5 | 0.5
| Research : Bill of lading | Corey | 1 | 1
| Develop Solution Plan : Bill of lading | Corey | 2.5 | 2.5
| Research : Trailer Tracking Methods | Corey | 1.5 | 1.5
| Develop Solution Plan : Available Parking | Corey | 2.5 | 2.5
| Develop Solution Plan: After Hours Arrivals | Corey | 1 | 1
| Develop Solution Plan : Overdue trailers | Corey | 1.5 | 1.5
| Develop Solution Plan : Broken Seal | Corey | 1 | 1
Totals |  |  | 11.5 | 11.5